## Project Management
Project Number
Project Name
Project Description
Project Level | A |  |  | A - All new, B - Innovaition, C- Cosmetics
Priority |  |  |  | Project priority for each customer
Customer
Target FOB
Forecasted Annual Quantity | Year 1 | Year 2 | Year 3
Shipment Deadline
SKLZ Project Lead
Jenkins Project lead | Weng Kin | wengkin@jenkins-asia.com | Tel: +86 1381 668 9550
Manufacturer Project Lead | To be Confirmed | To be Confirmed | To be Confirmed
Overall Status | Design Phase - Product Specifications
Phase | Deliverable | Responsibility | Deadline | Status | Jenkins Remarks | Customer Remarks | Team member | Estimated manhours per team member | Estimated manpower internal cost | Additional resources | Estimated additional resource internal cost
Market/Feasibility | Market Product Proposal | SKLZ
| Preliminary Cost | Jenkins Asia
Design | Product Specifications | Jenkins Asia |  | In Progress
| 3D Drawing | Jenkins Asia
| 2D Drawing | Jenkins Asia
| Costed BOM | Jenkins Asia
| Alpha Sample | Jenkins Asia
| Alpha Sample Review Report | Jenkins Asia
| Alpha costed BOM | Jenkins Asia
| Industrial Design | SKLZ |  | In Progress
| Beta Sample | Jenkins Asia
| Beta costed BOM | Jenkins Asia
| Beta Sample Review Report | Jenkins Asia
Test Requirements and standards (Functional, Reliability, Regulatory, Life, Production)
| Beta Sample Functional and Reliability Test Report |  | To be confirmed
Formal Engineering Drawing Package
Final Costing
Tooling | Production Tools
Trial Run Review (QS9000 PPAP)
Trial Assembly Review
| Quality Standards | Jenkins Asia and SKLZ
| Work Instructions (Standard Operating Procedures) | Manufacturer
| Packaging and Box Art | SKLZ
Packaging Review and Testing Report
| Instruction, Manuals and Warranty Card | SKLZ
| Regulatory Test Report | Manufacturer
| Life testing report | Manufacturer | To be confirmed
Mass Production | Pilot Production Review Report | Jenkins Asia and SKLZ
| Quality Inspection Training | Jenkins Asia and GTA
1st Shipment Review Report

## Costing
Project No | Customer Model Number | Jenkins Model Number | Customer Assembly Number | Customer Parent Assembly Number | Jenkins Assembly Number | jenkins parent Assembly Number | Customer part Number | Jenkins part Number | Customer Drawing Number | Revision | Jenkins Drawing Number | Revision | Internal Budgetary Price | External Budgetary Price | Internal Alpha Price | External Alpha Price | Internal Beta Price | External Beta Price | Internal Final Price | External Final Price | Quantity per Product
Internal Price Breakdown (Budgetary, Alpha, Beta, Final)
Project No | Customer Model Number | Jenkins Model Number | Customer Assembly Number |  | Jenkins Assembly Number |  | Customer part Number | Jenkins part Number | Customer Drawing Number | Revision | Jenkins Drawing Number | Revision | Material | Additional Material Specification | Finish | Material Cost | Assembly Cost | Overhead | Factory Profit | Tax | Customs | Freight | Handling | Internal Budgetary price
External Price Breakdown - data is copied from internal price breakdown by default but is overwritten
Project No | Customer Model Number | Jenkins Model Number | Customer Assembly Number |  | Jenkins Assembly Number |  | Customer part Number | Jenkins part Number | Customer Drawing Number | Revision | Jenkins Drawing Number | Revision | Material | Additional Material Specification | Finish | Material Cost | Assembly Cost | Overhead | Factory Profit | Tax | Customs | Freight | Handling | External Budgetary price | Approved | Published
[25 empty] | Y/N | Y/N
Project Costing per JKT07 - Project Control Sheet

## Task
Project Number | Phase | Deliverable | Responsibility | Task Number | Predecessor task number | Successor task number | Task Priority | Task Description | Responsible person | Start Date | End Date | Status | Status Detail | Attachment
[12 empty] | Not Started |  | Doc, pdf, excel, photo, video
In Progress
Late
Delayed
Postponed
On Hold
Completed

## Resources
Personnel ID | Personnel Name | Designation | Address | Home Phone |  | CellPhone | Home Email | Company Email | Skype ID | Location | % Loading (on 40hr week) | Open Task | Required Time | Completed task
Personnel ID:
| Day 1 | Day2 | [7 empty] | Day 3 | Day 4 | Day 5
Complete 3D drawing [genesys project] - In progress
Submit Quality Analysis [Orion project] - late
Submit test reports [trio project] completed
Complete 2D drawing [Orion project] - In progress
Loading | 80% | 80% | [7 empty] | 40% | 20% | 20%
Location | Home office | Home Office | [7 empty] | HQ | Kunshan Jinboa | Kunshan Jinboa
Factory ID | Factory Name | Website | Address | Contact Person 1/2/3 | Designation 1/2/3 | Phone 1/2/3 | CellPhone 1/2/3 | Email 1/2/3 | Skype ID 1/2/3 | Project No | Open Task | Closed Task | Open Order | Shipped Orders | Open Delivery | Shipped Delivery | Open Complaints | Closed Complaints | Scorecard (Price * Delivery * Quality)

## Documentation
Report Input Forms
Existing Forms
JKT01 - Corrective Action Form
JKT02 - Request for Budgetary Quote
JKT03- Supplier General process Audit Plan
JKT04 - Supplier Initial Quality Survey Form
JKT05 - Supplier Process Audit plan
JKT06 - Supplier Survey
JKT07 - Project Control Sheet
JKT08 - Sample Review Form
JKT09 - Customer Quote
JKT10 - Non Disclosure Agreement
Additional Documents/Attachments
Enginering Drawings (Pro-E, Solidworks, AutoCAD,
Project Proposals
Agreement Contracts
Factory quotes
Product Specifications
Additional Forms to be added into the database
Engineering change notice
Task Request - (See Task sheet)
Root Cause Failure analysis
Project Specifications (See sheet project Management)
Project Number | Phase | Deliverable | Document Title | Customer/Supplier Document Number | Jenkins Document Number | Document Description | Form Data | Attachment | Issued by | Issue Date | Approved By | Approval Date | Revised By | Revision Date | Revision | Revision History | Keywords
Per form format

## ECR - Cover Page
Engineering Change Request
|  |  |  | Dropdown Value for Cell B4 | Suggested Prefixes for Cell B5 | Dropdown Value for Cell B6
Title | Enter Title here |  |  | Category | Request Number | Request Code
Change Category |  |  |  | [Change Request] | CAR | Cost
Request Number | [Enter Number here] |  |  | Compliance Change Request | CCR | Performance
Request Code |  |  |  | Document Change Request | PCR | Manufacturability
Description of problem | (Describe problem including both scope and impact below) |  |  | Engineering Change Request | DEVR
|  |  |  | Manufacturing Change Request | ECR
|  |  |  | Process Change Request | FFR
|  |  |  | Corrective Action Change Request | MCR
|  |  |  | Field Failure Request | NCMR
|  |  |  | Non-Conformance Material Request | NPCR
|  |  |  | Obsolescence Notice | OBSN
Solution Requirements |  |  |  | [Supplier Request] | PCR
|  |  |  | Request for Quotation | RFQ
|  |  |  | Supplier Corrective Action Request | SCAR
Creator |  | Creator's Signature
Created Date | / /
Supporting Documents
Document # | Title
Disposition | (Circle one below and provide explanation for action.)
Approve | Defer |  | Reject
Associated Change Orders
[Enter ECO # here] | [Enter Name here]
Evaluators
Name: |  | Department:
Name: |  | Department:
Name: |  | Department:
Name: |  | Department:

## ECR - Items Impacted
Engineering Change Request
Title |  | Enter Title here
Request Number |  | [Enter Number here]
Impacted Items & Products List
Items impacted by possible change
# | Item Number | Item Name | Phase | Notes | Associated Documents
1 |  |  |  |  | Customer Drawing numbers and Jenkins Drawing Numbers
2
3
4
5
Products impacted by possible change (List top-level parent(s) of items referenced above in the rows below)
# | Item Number | Item Name | Phase | Notes | Associated Documents
1
2
3
4
5

## ECN
Engineering Change Notice
Note: this is usually sent to supplier
ECN Number:
From: | Company initiating change
To: | Supplier or CM to be notified |  | Date of Notice: | / /
ECO Number: |  |  | ECO Approval Date: | / /
Change | Describe in detail
Reason | Describe in detail
Items Impacted
Item # | Title | Disposition
Actions Requested
Authorized by:
Name: |  | Date:
Signature: |  | Email:
__________________________________
Company
Logo

## Order tracking
Project Number | Customer PO Number | Attachment | Compliance | Jenkins PO Number | Attachment | Factory | Terms | Account Payment | Customer model number | Customer part Number | Jenkins model number | Jenkins Part Number | Internal Final price | External Final price | Quantity | Total Amount | Currency | Delivery Date 1 | Delivery Status 1 | Delivery Date 2 | Delivery Status 2 | Payment 1 Schedule | Payment 1 status | Attachment | Payment 2 schedule | Payment 2 status | Attachment | Payment 3 schedule | Attachment | Payment 3 status | Final Total Amount Received
[19 empty] | In Progress |  |  |  | Not Paid
[19 empty] | Delayed |  |  |  | In Process
[19 empty] | Late |  |  |  | Received
Canceled
On Hold
Compliance is a checkbox
When a new order is entered, the Compliance box is a drop down menu with an option to enter extra fields
Default Drop down data
Customer Quality Test/Inspection
Third Party Test/Inspection
Jenkins Quality Inspection
ETL
CE
FCC
ISF
CPSC
ROHS
REACH
The selected options will become check boxes that must all be checked before the order can ship

## Security levels (Access Control
Customer | level 1 | direct customer | own project status & external prices
| level 2 | indirect customer | involved tasks only
Supplier | level 1 | direct supplier | own project status and quote submission only
| level2 | indirect supplier | involved task only
Personnel | Admin |  | all database, no access to any costing or prices
| level 1 | management | all database
| level 2 | middle management | all project status & internal prices only
| level 3 | staff | own project status & internal prices only

## Communication
Communication - Discussion thread (BBS style)
Link | Title | Comment | Attachment | Commenter | Comment Date | Comment to
Link to any part of the database
Communications - Automatic email Notifications
Status changes (e.g. In progress to late)
New project/task assigments
New comments
New requests
New updates/revisions
New customer complaints
Communications - Manual Email notifications
Quotes to customer
Purchase Order Issue (PO's)
Request for Quotations to factories/suppliers

## Sample management
Project No | Customer Model Number | Jenkins Model Number | Customer part Number | Jenkins part Number | Customer Drawing Number | Revision | Jenkins Drawing Number | Revision | Sample Level | Quantity | Sample number | Sample Location 1/2/3/4/5 | Sample fabricator | Sample date | Sample Cost | Sample Order Number (PO number) | Jenkins Approved by | jenkins Approval date | Customer Approved | Customer Approval date
[9 empty] | Conceptual |  |  | Depending on number of samples | [6 empty] | y/n
Alpha
Beta
Trial
Production
Golden

## Knowledge management
Search feature

## Financial Tracking
Incoming Payment Amount | Customer/Source | Outgoing payment Amount | Beneficiary | Project Number | PO Number | Invoice Number | Reason | Planned Incoming Payment Date | Actual Incoming Payment Date | Difference | Incoming Payment Status | Actual Incoming Payment Amount Received | Planned Outgoing Payment Date | Actual Outgoing Payment Date | Difference | Outgoing Payment Status | Actual Outgoing Payment Amount Paid

## Quality Main
SCA Number | Customer | Customer Project Number | Customer PO Number | Jenkins Project Number | Jenkins PO Number | Corrective Action Number | Supplier | Raised By: | Raise Date | Category | Priority | Status | Closure Time
Functional
Cosmetic
Safety

## Quality Pg 1
Corrective Action No: | TIANFU110001
Issue Date: | 9/21/2011
Supplier | Tianfu
Product No. | PMH
Product Description | Pro Mini Hoop
Shipment Number (Or tracking No.)
Lot Quantity | 5
Sample Size | 5
Defects found | 3
Reject Rate (%) | 60
Quantity in Inventory | 300
Quantity in Process | 2000
Containment Disposition | 100% Sort
Acknowledge By (Supplier) | Tianfu
Acknowledge Date | 2011-09-22
Verified for Closure By
Verification Date
This is the main page of every complaint . The details of the complaint is captured in Quality Pg 2

## Quality Pg 2
No. | Reject Description | Category [Drop down box] | Quantity | Attach Picture (if applicable) | Required Disposition | Root Cause | Containment Action | Supplier Short Term Corrective Action | Implementation Date | Verified | Supplier Long Term Corrective Action | Implementation Date | Vendor Process Audit Plan Revision | Verified
1 | Scratches on the upper surface of PC board | Cosmetic | 3 of 5 | NA | Scrap Rejects | a. Didn’t use soft foam to separate each board after cutting. b. Foot print is caused when assemble door hook and screws in production line. Mopping with white gloves caused more scratches on upper surface. | 100% Sort | Check all the assembled products to find out if there is scratch or bad pad printing.Scrap all the defective parts. | 2011-09-22 |  | 1. IPQC needs to check the scratches before pad printing for future production. 100%. 2. IPQC needs to check the pad printing and scratches before put the foam on for future production. 100%. 3. Need to test out if the footprint can be cleared with pledget. | 2011-09-22 | N
2 | Spot welding of rim hook is bad. Missing welding and exceeding welding. | Functional | 1 of 2 |  | Rework Rejects | QC didn't check 100% | 100% Sort | Check all the assembled products to find out if there is missing welding or exceeding welding.Scrap all the defective parts. | 2011-09-22 |  | IPQC needs to check the rim 100% on line for future production. | 2011-09-22 | N

## Quality - Supplier Scorecard
Supplier | Total Orders | No. of On time delivery | No. of late delivery | AVG Late time | No. of Corrective Actions (Complaints) | AVG Closure time | Total Ship Quantity | Total Ship Monetary Amount | Total No. of Rejects | Ranking

## Naming Conventions
Jenkins Online Operation System | JOOS
Jenkins Project Management System | JPMS
Jenkins Asia Online System | JAOS
Jenkins Asia Web System | JAWS
Jenkins Asia Web Administration | JAWA
Jenkins Asia Web Support | JAWS
Jenkins Asia Management System | JAMS
Jenkins Asia Networked Operations Support | JANOS
Jenkins Asia New Online System | JANOS
Jenkins Asia Networked User System | JANUS
Jenkins Asia Networked User Support | JANUS
Jenkins Asia Networked Operations System | JANOS
Jenkins Asia Networked Organization System | JANOS
Jenkins Asia Networked Utilities System | JANUS
Jenkins Asia Networked Utilities Software | JANUS
Jenkins Asia Networked Engineering Terminal | JANET
Jenkins Asia Networked Engineering Tool | JANET
Jenkins Asia Networked Engineering Tracking | JANET
Jenkins Asia Networked Enterprise Tool | JANET