## BallBike Home Magnetic Schedule
Phase | Deliverable | Resp | Deadline | Status | Jenkins Remarks | Fitone Remarks
Market/Feasibility | Market Product Proposal | Fitone | 2011-12-23
| Preliminary Cost | Jenkins Asia | 2011-12-30 |  | 16 man hours - requires pre-design and 3D prior to discussion with suppliers (mainly with the lock system)
Design | Product Specifications | Jenkins Asia | 2011-12-30 |  | 8 man hours - this will need to be done prior for preliminary costing as well because this product is very different from any other product.
| Industrial Design | Fitone | 2012-01-13
| 3D | Jenkins Asia | 2012-01-20 |  | 80 man hours
| 2D | Jenkins Asia | 2012-02-26 |  | 40 man hours (Chinese new year)
| Costed BOM | Jenkins Asia | 2012-02-26 |  | 24 man hours
| Alpha Sample | Jenkins Asia | 2012-03-11 |  | 20 man hours
| Alpha Sample Review Report | Jenkins Asia | 2012-03-12 |  | 4 man hours
| Alpha costed BOM | Jenkins Asia | 2012-03-18 |  | 4 man hours
| Beta Sample | Jenkins Asia | 2012-04-01 |  | 20 man hours
| Beta costed BOM | Jenkins Asia | 2012-04-01 |  | 24 man hours
| Beta Sample Review Report | Jenkins Asia | 2012-04-08 |  | 4 man hours
| Test Requirements and standards (Functional, Reliability, Regulatory, Life, Production) | Jenkins Asia and Fitone | 2012-04-01 |  | 16 man hours
| Beta Sample Functional and Reliability Test Report | Kunshan Jinboa | 2012-05-31 |  | 8 man hours
| Formal Engineering Drawing Package | Jenkins Asia | 2012-04-22 |  | 40 man hours
| Final Costing | Jenkins Asia and Kunshan Jinboa | 2012-04-29 |  | 8 man hours - This is the final step in the upfront engineering. After final costing is greenlit, the tool fabrication would begin.
Tooling | Production Tools | MFG | 2012-06-28
| Trial Run Review (QS9000 PPAP) | Jenkins Asia and Kunshan Jinboa | 2012-07-05 |  | 16 man hours
| Trial Assembly Review | Jenkins Asia and Kunshan Jinboa | 2012-07-19 |  | 24 man hours
| Quality Standards | Jenkins Asia and Kunshan Jinboa | 2012-06-28 |  | 24 man hours
| Work Instructions (Standard Operating Procedures) | Kunshan Jinboa | 2012-07-05
| Packaging and Box Art | Fitone | 2012-04-29
| Packaging Review and Testing Report | Kunshan Jinboa | 2012-04-29
| Instruction, Manuals and Warranty Card | Fitnone | 2012-04-29
| Regulatory Test Report | Kunshan Jinboa | To be confirmed |  | This will be subject to test requirements
| Life testing report | Kunshan Jinboa | To be confirmed |  | This will be subject to test requirements
Mass Production | Pilot Production Review Report | Jenkins Asia and Kunshan Jinboa | 2012-08-04 |  | 24 man hours. Alternatively, if there are no issues with the Alpha Sample, the time can be reduced by 1.5 months and be done by end June
| Quality Inspection Training | Jenkins Asia | 2012-08-04 |  | 40 man hours
| 1st Shipment Review Report | Fitone | 2012-09-13
Formulas:
Deadline = [Deadline, row above]+14
Deadline = [Deadline, row above]+7+30