## Sheet1
Sequence | Working Item | Working load(man/day) | Ammount(K/RMB) | Description
1 | Requirement analize | 10 | 10
2 | Write use case document | 5 | 2
3 | Drawing mockup | 5 | 2
4 | Software development | 150 | 40 | 1. Technigue investigation 2.Data table redesign 3.Refactor system base structor to support new data table. 4.Including module testing work
5 | software integration testing | 10 | 2
6 | Software deployment | 5 | 4
60
Note on H13: 蓝色单元格自动计算，请勿填写。